## Sheet1
Status | Date Completed | Task ID | Description | Type | Priority | For Phase | Path | Commit Message | Has FE Changes | Has BE Changes | Remarks
|  |  | A user should be able to have multiple accounts (e.g. one as a player and another as a coach) |  | Low | 2
|  |  | Court Details - Put hourly rate inside the Book/Reserve button | Design | Low | 1
|  |  | Use a better time picker | Improv | Low | 1
|  |  | Map - Add control to go to current location | Feat | Low | 1
|  | WEB-0011 | Add “Talk to us” link to FB page | Feat | Low | 1
|  | WEB-0042 | Courts – use featured courts as background instead of a static bg image. Also autoscroll thru featured courts | Feat | Low | 1
|  | WEB-0100 | Upgrade Web API to .net Core 2.2 | Setup | Low | 1
|  |  | Game Reviews - Getting error when removing pricecomponent | Bug | Low | 1
|  | WEB-0010 | Fix issue: toolbar items get set multiple times when logging in and out of the app because toolbars onSetItems handler gets registered everytime it is initialized | Bug | Low | 1
|  |  | Map - user custom marker icon for courts | Improv | Low | 1
|  |  | Implement messaging feature | Feat | Low | 1
|  |  | Allow uploading of photo via url | Feat | Low | 1
|  |  | Court Viewer - Add "Make a reservation" button | Feat | Low | 2
|  | WEB-0097 | Account Viewer - Display a list of bookings made by a user | Feat | Low | 2
|  |  | Delete ng-form-extensions if not used | refactor | low | 1
|  |  | User Stub - clicking the icon takes user to Account Details instead of Account Home | Bug | Low | 1
|  |  | Group photos and videos as Media | Improv | Medium | 1
|  |  | Create separate version of photos for thumbnail | Improv | Medium | 1
|  |  | Scale down things (text, thumbnails, container height, etc) | Improv | Medium | 1
|  |  | Display court's city on thumbnail | Improv | Medium | 1
|  |  | Court Photos - Add function gets called twice when clicking on the Upload link | Bug | Medium | 1
|  |  | AccountViewer - Home - Display user's activities | Feat | Medium | 1
|  |  | Make sure all methods called by Web API are async | Improv | Medium | 1
|  |  | Court Details - Edit profile photo button is misplaced when ung Edge | Bug | Medium | 1
|  | WEB-0071 | Allow user to set City | Feat | Medium | 1
|  | WEB-0018 | Fix bug: a place is returned by map autocomplete when inputing “la kdfld” and pressing enter, even when there is no selected suggestion | Bug | Medium | 1
|  | WEB-0077 | Implement Email update on Account Settings Page | Feat | Medium | 1
|  |  | Court Search - Add the following options on the left panel - Browse All Court - Courts Near Me - Followed Courts - Featured Courts | Feat | Medium | 1
|  |  | When displaying multiple overlapping modals, the back button closes the modals in the back first | Bug | Medium | 1
|  |  | Court Viewer - Schedule - Error when scheduling a game: The INSERT statement conflicted with the FOREIGN KEY constraint "FK_dbo.Events_dbo.Courts_CourtId". The conflict occurred in database "dribbly_auth", table "dbo.Courts", column 'Id'. The statement has been terminated | Bug | Medium | 1
|  |  | Display error message from server side | Feat | Medium | 1
|  |  | Permission on other tabs don't get updated when user logs out. Also permission are not persisted between reloads | Bug | Medium | 1
|  |  | Court Photos - Current Primary photo should not be deletable | Bug | Medium | 1
|  |  | Set what will be seen on FB when a user page is shared | Feat | Medium | 1
|  |  | Set what will be seen on FB when a court page is shared | Feat | Medium | 1
|  |  | Upload Video modal - dialog filter does not work when changing the file | Bug | Medium | 1
|  |  | Prevent videos from downloading when displaying them as thumbnail | Bug | Medium | 1
|  |  | Court Viewer - Unhandled error when court ID does not exist | Bug | Medium | 1
|  |  | Account Viewer - Display appropriate message when account is not found | Improv | Medium | 1
|  |  | Handler 403 error in common service (e.g. show message saying that the user doen't have the required permission) | Feat | Medium | 1
|  |  | Add form validation messages. Forms: - Add/Edit Court Details - Book Game Form - Login Form - User Registration Form | Feat | Medium | 1
|  |  | Preview game details as read-only with an option to edit the details | Improv | Medium | 1
|  |  | Imprlement paging when displaying lists of courts, photos, videos, etc | Feat | High | 1
|  |  | Add functionality to Edit and Delete reviews | Improv | Medium | 1
|  |  | Account Home - Posts - As an account owner I should be able to hide any posts from my home page | Feat | Medium | 1
|  |  | Refactor - AccountsService - Rename async methods to include "Async" postfix | Refactor | Medium | 1
|  |  | Server-side Code - Move PhotoModel to appropriate namespace | Refactor | Medium | 1
|  |  | Video Thumnail and Player - Display video description | Feat | Medium | 1
|  |  | Move logic code from AccountsController to AccountsService | Refactor | Medium | 1
|  |  | Start notification checks on login using login modal | Improv | Medium | 1
|  |  | Post Details modal - Ctrl + Enter should submit the post | Improv | Medium | 1
|  |  | Add functionality to transfer ownership of a court | Feat | Medium | 1
|  |  | Placeholder of typeahead does not display fully even when there's enough space left inside the textbox | Bug | Medium | 1
|  |  | As a game creator, I should be able to modify the status of a finished game | Feat | High | 1
|  |  | When an error occurs in the server, do not return sensitive data about the error to the client (i.e. log error in the server and then return a friendly data to the client. Also include data that can be used to trace the error log created in the server) | Improv | High | 1
|  |  | Show confirmation dialog when starting and ending a game | Improv | High | 1
|  |  | When Join Team Request is cancelled, the notification created for that request should be deleted | Bug | High
|  |  | Log user activity when user leaves a team | Bug | High | 1
|  |  | Text Editor Component - Toolbar is transparent, doesn't look good on black container. Also, add options to show/hide controls | Improv | High | 1
|  |  | Show a "loading" indicator when the app is loading for the first time | Improv | High | 1
|  |  | As a user I should be able to Follow/Unfollow other accounts | Feat | High | 1
|  |  | Secure remaining unsecured actions | Improv | High | 1
|  |  | Account Videos - Add option to update and delete videos | Feat | Medium | 1
|  |  | Account Settings - As an account owner I should have the option to restrict who can post on my home page | Feat | Medium | 1
|  |  | Temporarily disable posting on other players' home page | Feat | Medium | 1
|  | WEB-0096 | Court Viewer - Photos - Allow user to use a photo from his gallery as Primary Photo | Feat | High | 1
|  | WEB-0093 | Allow user to view a list of courts that he/she registered | Feat | High | 1
|  | WEB-0033 | Court Edit – Modal title is wrong | Bug | High | 1
|  |  | Refactor API to use a different instance of DbContext for every call | Improv | High | 1
|  |  | Display Game Details | Feat | High | 1
|  |  | Add an option to remove a court | Feat | High | 1
|  |  | Add ability to rate a player | Feat | High | 1
|  |  | Log total number of visits and number of active sessions | Feat | High | 1
|  |  | Add functionality to share player profile on social platforms | Feat | High | 1
|  |  | Add ability to add Game comments | Feat | High | 1
|  | WEB-0089 | Finish View Account Details Design | Design | High | 1
|  |  | Add functionality to reactivate courts | Feat | High | 1
|  |  | Court Details - After updating court details, new court name is not reflected | Bug | High | 1 | /court/5/details
|  |  | Implement Global Search functionality - Create another table to be used for indexing all searchabled entities (e.g. Accounts, Courts, Games, Posts, etc.) | Feat | High | 1
|  |  | App Navigator - Active item is not highlighted | Bug | Medium | 1
|  |  | Show currently logged in user's name on the navigation bar | Improv | High | 1
|  |  | Error code 500 causes navigation to Login when it shouldn't (Probably resolved already) | Bug | Medium | 1
|  | WEB-0091 | Add option to Remove an account | Feat | Critical | 1
|  |  | Use SSL | Feat | High | 1
|  |  | When notification item for new booking is clicked it doesn't display the game's detail | Bug | Medium | 1
|  |  | Null Court Ratings are causing error | Bug | High | 1
|  |  | Make Home the defualt state when clicking link to a user | Improv | High | 1
|  |  | Record Account Reactivation user activity when logging in using a deactivated account | Feat | Medium | 1
|  |  | Empty comments should not be allowed | Bug | High | 1
|  |  | When a new game is set, create a post on court's home and on the home of the player who set the game | Feat | High | 1
|  |  | As a user I should be able to Join/Leave a team | Feat | High | 1
|  |  | As a user I should be able to Follow/Unfollow a team | Feat | High | 1
|  |  | Web API - input data is not being logged when an exception occurs during a POST request. LogsService.TryGetRequestData fails to read the input data | Bug | High | 1
|  |  | Notifications Pop Up - Not loading more items | Bug | High | 1
|  |  | Add functionality to rate a player | Feat | High | 1
Done | 2021-12-07 | WEB-0197 | Notifications are not generated when adding a new game Cause: Code is trying to generate a new BOOKING notification instead of new GAME notification | Bug | Critical | 1 |  | fix: WEB-0197 - ISSUE: Notifications are not generated when adding a new game | N | Y
Done | 2021-11-27 | WEB-0196 | Getting "$.resolve is not a function" error in the console | Bug | Medium | 1 |  | fix: WEB-0196 - fix "$.resolve is not a function error" and added some comments in notificationsService for documentation | Y | N
Done | 2021-11-27 | WEB-0195 | Account Home - Nothing happens when change primary photo is clicked | Bug | Critical | 1 |  | fix: WEB-0195 - fix change account primary photo functionality | Y | N
Done | 2021-11-27 | WEB-0194 | Exception occurs when joining a team | Bug | High | 1 |  | fix: WEB-0194 - fix issue: exception occurs when joining a team | N | Y
Done | 2021-11-27 | WEB-0193 | New courts are not being added to IndexedEntities table | Bug | Critical | 1 |  | fix: WEB-0193 - fix issue: new courts are not being added to IndexedEntities table | N | Y
Done | 2021-11-27 | WEB-0192 | Add dbo._DevHelpers_SP_DeleteUserByUserName | Setup | Medium | 1 |  | setup: WEB-0192 - dbo._DevHelpers_SP_DeleteUserByUserName | N | Y
Done | 2021-11-27 | WEB-0191 | Google map functionalities are not working | Bug | Critical | 1 |  | fix: WEB-0190 - update google Map API key | Y | N
Done | 2021-11-27 | WEB-0190 | Facebook login is not working | Bug | Critical | 1 |  | fix: WEB0190 - fix Facebook login functionality | Y | Y
Done | 2021-11-27 | WEB-0189 | Upgrade Web Client to AspNetCore 3.1 | Setup | High | 1 |  | setup: WEB0189 - Upgrade Web Client to AspNetCore 3.1 | Y | N
Done | 2021-03-14 02:37 | WEB-0188 | As a game creator, I should be able to re-open a cancelled game | Feat | High | 1 |  | feat: WEB-0188 - add functionality to re-open a cancelled game | Y | Y
Done | 2021-02-18 16:50 | WEB-0187 | As a game creator, I should be able to end a game | Feat | High | 1 |  | feat: WEB-0187 - implement cancel game functionality | Y | Y
Done | 2021-02-07 04:29 | WEB-0186 | As a game creator, I should be able to update game result | Feat | High |  |  | feat: WEB-0186 - implement update game result functionality | Y | Y
Done | 2021-01-31 23:43 | WEB-0185 | As a game creator, I should be able to start a game | Feat | High | 1 |  | feat: WEB-0185 - implement start game functionality | Y | Y
Done | 2021-01-29 03:56 | WEB-0184 | Generate teams when creating a new game | Feat | High | 1 |  | feat: WEB-0184 - Generate teams when creating a new game | Y | Y
Done | 2021-01-17 15:05 | WEB-0183 | As a team manager, I should be able to set the team's logo | Feat | HIgh | 1 |  | feat: WEB-0183 - Add functionality to update team's logo | Y | Y
Done | 2021-01-11 11:34 | WEB-0182 | Display competing teams in game details | Feat | High | 1 |  | feat: WEB-0182 - Display competing teams in game details | Y | Y
Done | 2020-12-21 03:52 | WEB-0181 | Add JsDoc | Setup | High | 1 |  | setup: WEB-0181 - add jsdoc
Done | 2020-12-16 07:48 | WEB-0180 | Game Details modal - add field to set court | Improv | High | 1 |  | improv: WEB-0180 - Game Details modal - add field to set court
Done | 2020-12-15 07:42 | WEB-0179 | Add function to crop profile photo to a rectangular shaped before uploading to server and modify Account Home to display photo as rectangel | Feat | High | 1 |  | - feat: WEB-0179 - add functionality to crop primary photo before uploading - improv: WEB-0179 - redesign account home
Done | 2020-12-05 09:57 | WEB-0178 | As a team manager, I should be able to Approve/Reject member requests | Feat | High | 1 |  | feat: WEB-0178 - add functionality to approve/reject join team requests
Done | 2020-12-05 09:26 | WEB-0177 | Team Members - Display team members and membership requests | Feat | High | 1 | /team/{teamId}/members | - feat: WEB-716 - Display current team members - feat: WEB-0716 - Display member requests
Done | 2020-12-01 04:42 | WEB-0176 | Team Manager should be able to join and leave the team | Feat | High | 1 |  | feat: WEB-0176 - add functionality for team manager to join and leave the team
Done | 2020-11-30 04:30 | WEB-0176 | Generate notification for team owner when someone requests to join the team | Feat | High | 1 |  | feat: WEB-0176 - generate notification for team owner when someone requests to join the team
Done | 2020-11-29 14:52 | WEB-0176 | As a user I should be able to send a request to join a team or cancel my request | Feat | High | 1 |  | feat: WEB-1076 - add functionality to create/cancel a request to join a team
Done | 2020-11-29 00:31 | WEB-0175 | GameModel does not have an entityStatusEnum property | Bug | High | 1 |  | fix: WEB-0175 - Add EntityStatus property to GameModel and rename Status property to EntityStatus of other entity models
Done | 2020-11-28 23:36 | WEB-0174 | Add functionality to create a team and display basic info | Feat | High | 1 |  | feat: WEB-0174 - Add functionality to create a team and display basic team info
Done | 2020-11-24 07:24 | WEB-0173 | Ass an account owner, I should be able to update my account's details | Feat | High | 1 |  | - feat: WEB-0173 - add ability to update account details - feat: WEB-0173 - add ability to set Player's home court - feat: WEB-0173 - display Account's home court - feat: WEB-0173 - Update IndexedEntities when an entity is updated | Y | Y
Done | 2020-11-23 01:35 | WEB-0172 | Posts - Place header inside a box to make design uniform | Design | High | 1 |  | design: WEB-0172 place header inside a box to make design uniform | Y | N
Done | 2020-11-17 18:22 | WEB-0171 | Court Details - Improve court design | Design | High | 1 |  | design: WEB-0171 - improve court details design | Y | N
Done | 2020-11-16 16:07 | WEB-0170 | Scroll to top when navigation occurs | Improv | Critical | 1 |  | improv: WEB-0170 - scroll to top when navigation occurs | Y | N
Done | 2020-11-16 16:07 | WEB-0169 | Court Home - Display location on a map | Feat | High | 1 |  | improv: WEB-0169 - display location on a map
Done | 2020-11-16 12:27 | WEB-168 | Game Viewer - When court is clicked open court preview modal instead of redirecting to court page | Improv | Medium | 1 |  | improv: WEB-0168 - preview court when name is clicked | Y | Y
Done | 2020-11-16 12:01 | WEB-167 | Court Home - As a court owner I should be able to update my court's description | Feat | High | 1 |  | feat: WEB-167 - add ability to edit court description from home page | Y | N
Done | 2020-11-15 18:39 | WEB-166 | Add Court Home page | Feat | High | 1 |  | feat: WEB-166 - add Court Home page | Y | N
Done | 2020-11-15 12:13 | WEB-0165 | As a court owner and admin, I should be able to delete a court | Feat | High | 1 |  | feat: WEB-0165 - add ability for court owner and admin to delete a court | Y | Y
Done | 2020-11-13 07:42 | WEB-0164 | Authentication data is not populated correctly before app starts | Bug | High | 1 |  | fix: WEB-0164 - fix issue with populated authentication data | Y | N
Done | 2020-11-13 06:59 | WEB-0163 | Redirect user to login page after logging out | Improv | High | 1 |  | refactor: WEB-0163 - redirect user to Login page after logging out | Y | N
Done | 2020-11-12 16:42 | WEB-0162 | Booking Details modal - Booked by input field - unable to retrieve suggested users | Bug | medium | 1 |  | fix: WEB-0162 - fix error when trying to retrieve suggested users | N | Y
Done | 2020-11-12 16:08 | WEB-0161 | Error when setting account primary photo | Bug | High | 1 |  | fix: WEB-0161 - fix error when setting account primary photo | N | Y
Done | 2020-11-12 16:04 | WEB-0160 | Change Identity user key type from string to int | Refactor | Critical | 1 |  | - refactor: WEB-0160 - update Identity models and non-app-specific code - refactor: WEB-0160 - update tables dependent to Identity Tables - refactor: WEB-0160 - make AspNetUser and UserRoles tables Id column auto increment - refactor: WEB-0160 - parse userId to int (UI only) | Y | Y
Done | 2020-11-11 09:21 | WEB-0159 | Log user activities | Feat | High | 1 |  | - feat: WEB-0159 - implement logging of Accounts and Posts-related user activities - feat: WEB-0159 - implement logging of contact-related user activities - feat: WEB-0159 - implement logging of court-related user activities and did some refactoring - refactor: WEB-0159 - remove unused enum member - feat: WEB-0159 - implement logging of game-related user activities - feat: WEB-0159 - add test | N | Y
Done | 2020-11-08 03:47 | WEB-0158 | Post Component - Secure Edit and Delete buttons | Improv | High | 1 |  | improv: WEB-0158 - post component - Secure Edit and Delete buttons | Y | Y
Done | 2020-11-08 03:46 | WEB-0157 | Utilize new global error handling pattern | Improv | High | 1 |  | improv: WEB-0157 - Utilize new global error handling pattern | Y | Y
Done | 2020-11-08 03:42 | WEB-0156 | Post Component - Commit files that were forgotten to be commited | Refactor | High | 1 |  | refactor: WEB-0156 - posts component - Commit files that were forgotten to be commited | Y | N
Done | 2020-11-07 14:33 | WEB-0155 | Improve global error handling | Improv | Critical | 1 |  | feat: WEB-0155 - Improve global error handling | Y | Y
Done | 2020-11-03 04:02 | WEB-0154 | Account Details - Add functionality to create, display, edit, and delete posts | Feat | High | 1 |  | feat: WEB-0154 - move post details to a separate component (UI Only) feat: WEB-0154 - Add functionality delete posts feat: WEB-0154 - Impelement Post Editing functionality feat: WEB-0154 - Add functionality to create and display posts | Y | Y
Done | 2020-11-02 00:45 | WEB-0153 | Error when opening notifications pop up: Date.toUTCString is not a constructor at Object.getUtcNow (datetime.service.js:61) | Bug | High | 1 |  | fix: WEB-0153 - fix error when opening notification pop up | Y | Y
Done | 2020-11-01 23:48 | WEB-0152 | Court Games - End time displays as nullZ if null | Bug | Medium | 1 |  | fix: WEB-0152 - fix display of null dates | Y | N
Done | 2020-11-01 09:15 | WEB-0151 | Home - Fails to load without internet connection due to google maps API | Bug | High | 1 |  | bug: WEB-0151 - fix google maps API error | Y
Done | 2020-11-01 09:12 | WEB-0150 | Game Details - Implement Update Game Details | Feat | Medium | 1 |  | feat: WEB-0150 - Implement Update Game Details | Y | N
Done | 2020-11-01 06:40 | WEB-0149 | Game Details - Improve display of Game details | Feat | Medium | 1 |  | design: WEB-0149 - make design improvements
Done | 2020-11-01 06:40 | WEB-0148 | Separate Reservation and Game | Improv | High | 1 |  | -refactor: WEB-0148 - Rename GameBookedNotificationModel to NewBookingNotificationModel (API only) - refactor: WEB-0148 - Replace EventModel with BookingModel (API only) - refactor: WEB-0148 - rename CourtReviewModel property EventId to BookingId (API only) - refactor: WEB-0148 - rename notificationTypesEnum and update Court components (WEB only) | Y | Y
Done | 2020-10-18 09:49 | WEB-0147 | design: WEB-0147 - Update logo | Design | Medium | 1 |  | design: WEB-0147 - Update logo | Y | N
Done | 2020-10-18 09:47 | WEB-0146 | Account Viewer - Home - Add page and display the player's profile | Feat | High | 1 |  | feat: WEB-0146 - Account Viewer - Home - Add page and display the player's profile | Y | N
Done | 2020-10-18 05:36 | WEB-0145 | Add Court Reviews view and ability to post a review | Feat | Medium | 1 |  | feat: WEB-0145 - add Court Reviews view and ability to post a review | Y | Y
Done | 2020-10-11 | WEB-0144 | Update Game Details design | Improv | Medium | 1 |  | improv: WEB-0144 - Update Game Details design | Y | Y
Done | 2020-09-28 | WEB-0143 | Do not use custom scrolls on small screens | Improv | Low | 1 |  | Improv: WEB-0143 - Do not use custom scrolls on small screens | Y | N
Done | 2020-09-28 | WEB-0142 | Improve Account details page | Improv | Low | 1 |  | improv: WEB-0142 - Improve Account details page | Y | N
Done | 2020-09-20 | WEB-0141 | Show login modal when authentication fails mid-transaction | Improv | Medium | 1 |  | improv: WEB-0141 - Show login modal when authentication fails mid-transaction | Y | N
Done | 2020-09-20 | WEB-0140 | Search Court Modal - courts do not display on the map | Bug | High | 1 |  | fix: WEB-0140 - Corrected call to onMapReady function | Y | N
Done | 2020-09-20 | WEB-0139 | Add missing references for infinite scrolling | Bug | High | 1 |  | fix: WEB-0139 - Add missing references for infinite scrolling | Y | N
Done | 2020-09-20 | WEB-0138 | Validate user token on initial load | Improv | High | 1 |  | improv: WEB-0138 - refresh token upon initial load | Y | N
Done | 2020-09-20 | WEB-0137 | Design scrollbars | Improv | Medium | 1 |  | improv: WEB-0137 - implement global scrollbar design | Y | N
Done | 2020-09-03 17:55 | WEB-0136 | Implement notifications for Event bookings | Feat | Medium | 1 |  | - feat: WEB-0136 - Implement notifications for Event bookings - feat: WEB-0136 - Implement infinite scrolling for notifications dropdown - feat: WEB-0136 - go to game details when notification is clicked | Y | Y
Done | 2020-08-28 02:33 | WEB-0135 | Map Search Autocomplete - remove type restriction and improve search suggestions to show results near the currently viewed area | Improv | Medium | 1 |  | improv: WEB-0135 - Map Search Autocomplete - remove type restriction and improve search suggestions to show results near the currently viewed area | Y | N
Done | 2020-08-26 07:34 | WEB-0134 | Nearby Courts component improvements - Show error when location to access is denied - Implement infinite scroll functionality | Improv | Medium | 1 |  | - improv: WEB-134 - Show error when location to access is denied - improv: WEB-134 - Implement infinite scroll functionality
Done | 2020-08-24 16:39 | WEB-0133 | Court Details - Show nearby courts | Feat | Medium | 1 |  | feat: WEB-0133 - Court Details - Show nearby courts | Y | N
Done | 2020-08-24 14:51 | WEB-0132 | Courts Home - Display nearyby courts | Feat | Medium | 1 |  | feat: WEB-0132 - Courts Home - Display nearyby courts | Y | N
Done | 2020-08-23 09:27 | WEB-0131 | Convert Featured Courts list into a carousel | Improv | Low | 1 |  | improv: WEB-0131 - Convert Featured Courts list into a carousel | Y | N
Done | 2020-08-17 02:38 | WEB-0130 | Activate link to current users profile in the navigator and toolbar | Feat | Medium | 1 |  | feat: WEB-0130 - Activate link to current users profile in the navigator and toolbar
Done | 2020-08-17 00:09 | WEB-0129 | Account - Allow user to set an account as public or private | Feat | Medium | 1 |  | feat: WEB-0129 - Allow user to set an account as public or private | Y | Y
Done | 2020-08-08 20:18 | WEB-0128 | Account Details - Rename Sex to Gender | improv | Medium | 1 |  | improv: WEB-0128 - Account Details - Rename Sex to Gender
Done | 2020-08-08 18:42 | WEB-0127 | Format court follower count | Improv | Medium | 1 |  | improv: WEB-0127 - Format court follower count | Y | Y
Done | 2020-08-02 22:49 | WEB-0126 | Add Booked By field to Court details | Feat |  | 1 |  | - feat: WEB-0126 - create typeahead component - feat: WEB-0126 - add Booked By field and fix updating of game details | Y | Y
Done | 2020-08-01 12:05 | WEB-0125 | Court Details - Court Owner not showing | Bug |  | 1 |  | fix: WEB-0125 - Court Details - Court Owner not showing | N | Y
Done | 2020-07-28 15:24 | WEB-0124 | Add app navigator for Web version and make some spacing adjustments | Feat |  | 1 |  | feat: WEB-0124 - Add app navigator for Web version and make some spacing adjustments | Y | N
Done | 2020-07-28 11:41 | WEB-0123 | Add Account Photos page | Feat |  | 1 |  | feat: WEB-0123 - Add Account Photos page | Y | Y
Done | 2020-07-26 14:47 | WEB-0122 | Add an 'Add Court' button in home page for Web | Feat |  | 1 |  | feat: WEB-0122 - Add an 'Add Court' button in home page for Web | Y | N
Done | 2020-07-26 11:46 | WEB-0121 | Implement Follow/Unfollow court | Feat |  | 1 |  | feat: WEB-0121 - Implement Follow/Unfollow court | Y | Y
Done | 2020-07-25 13:11 | WEB-0120 | Implement Court details Contact button | Feat |  | 1 |  | feat: WEB-0120 - Implement Court details Contact button | Y | N
Done | 2020-07-25 13:09 | WEB-0119 | allow modal service alert to accept an object as options | Feat |  | 1 |  | feat: WEB-0119 - allow modal service alert to accept an object as options | Y | N
Done | 2020-07-25 11:39 | WEB-0118 | Implement mobile no. verification functionality | Feat |  | 1 |  | feat: WEB-0118 - Implement mobile no. verification functionality | Y | Y
Done | 2020-07-24 17:00 | WEB-0117 | Add mobile no. to court details and rename "Public" to "Free To Play" | Improv |  | 1 |  | improv: WEB-0117 - Add mobile no. to court details and rename "Public" to "Free To Play" | Y | Y
Done | 2020-07-18 07:29 | WEB-0116 | User permissions are lost when token expires even after token is successfully refreshed. | Bug |  | 1 |  | fix: WEB-0116 - persist user permission between page reloads after token has expired and has been successfully refreshed | Y | N | refreshToken function was not re-saving the permissions to local storage
Done | 2020-07-18 06:55 | WEB-0115 | Display appropriate error when login fails | Impov |  | 1 |  | improv: WEB-0115 - Display appropriate error when login fails | Y | N
Done | 2020-07-18 06:13 | WEB-0114 | When server calls fail, user is redirected to the login page even if the cause is not due to authorization | Bug |  | 1 |  | fix: WEB-0114 - When server calls fail, user is redirected to the login page even if the cause is not due to authorization | Y | N
Done | 2020-07-16 09:07 | WEB-0113 | Implement deletion of court videos | Feat |  | 1 |  | feat: WEB-0113 - Implement deletion of court videos | Y | Y
Done | 2020-07-16 09:03 | WEB-0112 | Improvements for uploading court videos: - Implement database rollback when an error occurs while add a court video - Add security check | Improv |  | 1 |  | feat: WEB-0112 - Add improvements for uploading court videos | Y | Y
Done | 2020-07-15 21:13 | WEB-0111 | Account Videos - Implement adding, viewing and playing of account videos | Feat |  | 1 |  | feat: WEB-0111 - Account Videos - Implement adding, viewing and playing of account videos | Y | Y
Done | 2020-07-14 21:12 | WEB-0110 | Court Videos - Upload date and time is incorrect | Bug |  | 1 |  | fix: WEB-0110 - Court Videos - Upload date and time is incorrect | Y | N
Done | 2020-07-13 11:47 | WEB-0109 | Implement playing of videos | Feat |  | 1 |  | feat: WEB-0109 - Implement playing of videos | Y | N
Done | 2020-07-13 03:41 | WEB-0108 | Add uploading and displaying court videos | Feat |  | 1 |  | feat: WEB-0108 - Allow users to upload videos | Y | Y
Done | 2020-07-07 10:14 | WEB-0107 | Court Details - Allow viewing of photos by click on the primary photo and deletion | Feat |  | 1 |  | feat: WEB-0107 - Court Details - Allow viewing of photos by click on the primary photo and deletion | Y | Y
Done | 2020-07-07 02:07 | WEB-0106 | Account Details - Allow deletion of photos while viewing photos by clicking on the profile photo | Feat |  | 1 |  | feat: WEB-0106 - Account Details - Allow deletion of photos while viewing photos by clicking on the profile photo | Y | Y
Done | 2020-07-06 01:21 | WEB-0105 | Account Detials - Allow viewing of primary photo by click on the primary photo | Feat |  | 1 |  | feat: WEB-0105 - Account Detials - Allow viewing of primary photo by click on the primary photo | Y | Y
Done | 2020-07-05 08:44 | WEB-0104 | Allow users to update their primary photo | Feat |  | 1 |  | feat: WEB-0104 - Allow users to update their primary photo | Y | Y
Done | 2020-07-05 08:00 | WEB-0103 | Allow displaying of options as a modal | Feat |  | 1 |  | feat: WEB-0103 - Add function to display options as a modal | Y | N
Done | 2020-07-04 20:38 | WEB-0102 | Can't navigate to court viewer by clicking View Full Details on Court Preview modal. Getting console errors | Bug |  | 1 |  | fix: WEB-0102 - Can't navigate to court viewer by clicking View Full Details on Court Preview modal. Getting console errors | Y | N
Done | 2020-06-30 19:52 | WEB-0101 | Implement global error handling in Web API | Feat |  | 1 |  | feat: WEB-0101 - Implement global error handling in Web API | Y | N
Done | 2020-06-26 | WEB-0099 | Move Services and Models to a separate project | Refactor |  | 1 |  | Refactor: WEB-0099 - Move Services and Models to a separate project Refactor: WEB-0099 - move models to a separate project Also: - Move Authentication-related files to a separate project | N | Y
Done | 2020-06-13 12:41 | WEB-0098 | Display error page when a fatal error occurs | Feat |  | 1 |  | feat: MSMT5-0098 - Display error page when a fatal error occurs | Y | N
Done | 2020-06-08 15:37 | WEB-0095 | Implement Error logging | Feat |  | 1 |  | feat: WEB-0095 - Impement error logging | Y | Y
Done | 2020-06-30 07:53 | WEB-0094 | Implement authorization | Feat |  | 1 |  | feat: WEB-0094 - Implement authorization | Y | Y
Done | 2020-08-15 23:42 | WEB-0090 | Add option to Deactive, reactivate and delete an Account | Feat | High | 1 |  | feat: WEB-0090 - Add option to Deactive and Re-activate Account | Y | Y
Done | 2020-06-08 16:05 | WEB-0088 | Display real owner name and avatar in court details | improv |  | 1 |  | improv: WEB-0088 - Display real owner name and avatar in court details | Y | Y
Done | 2020-06-01 07:14 | WEB-0087 | Upgrade to UI-Bootstrap 4 | Setup |  | 1 |  | setup: WEbB-0087 - Upgrade to UI-Bootstrap 4 | Y | N
Done | 2020-05-31 13:44 | WEB-0086 | Map - use our own search autocomplete component to allow it to work even when map is in full screen | Improv |  | 1 |  | improv: WEB-0086 - Map - use our own search autocomplete component to allow it to work even when map is in full screen | Y | N
Done | 2020-05-31 12:53 | WEB-0085 | Refactor localtion picker component to use custom map instead of NgMap | improv |  | 1 |  | improv: WEB-0085 - Refactor localtion picker component to use custom map instead of NgMap | Y | N
Done | 2020-05-31 10:00 | WEB-0084 | Map - Use native google map instead of NgMap in custom map component to have better control of the map | Improv |  | 1 |  | improv: WEB-0084 - Map - Use native google map instead of NgMap in custom map component to have better control of the map | Y | N
Done | 2020-05-31 08:50 | WEB-0083 | Map - Create custom map component with build-in search function and use in Court Search modal | Feat |  | 1 |  | feat: WEB-0083 - Map - Create custom map component with build-in search function and use in Court Search modal | Y | N
Done | 2020-05-25 23:37 | WEB-0082 | Use ContainerControlled lifetime when registering dependencies to Unity Container | Improv |  | 1 |  | improv: WEB-0082 - Use ContainerControlled lifetime when registering dependencies to Unity Container | N | Y
Done | 2020-05-25 07:12 | WEB-0081 | Move filter form to the right side of Court Search modal | Design |  | 1 |  | design: WEB-0081 - Move filter form to the right side of Court Search modal | Y | N
Done | 2020-05-25 06:43 | WEB-0080 | Court Search - Add sorting | Feat |  | 1 |  | feat: WEB-0080 - Add court sorting | Y | N
Done | 2020-05-25 03:08 | WEB-0079 | Allow browsing courts using a map Also: - Add filtering based on rate | Feat |  | 1 |  | feat: WEB-0079 - Allow browsing courts using a map | Y | N
Done | 2020-05-11 14:50 | WEB-0078 | Remove ID and DateAdded properties from BaseModel and move it to a new BaseEntityModel so that Models inheriting from BaseModel are not require to have Id and DateAdded, or to have to hide them | Refactor |  | 1 |  | refactor: WEB-0078 - Remove ID and DateAdded properties from BaseModel and move it to a new BaseEntityModel | N | Y
Done | 2020-05-11 14:40 | WEB-0076 | Implement Account Settings Page | Feat |  | 1 |  | feat: WEB-0076 - Add Account Settings page |  |  | Partial only
Done | 2020-05-18 02:15 | WEB-0075 | Implement finding courts by name | Feat |  | 1 |  | feat: WEB-0075 - Implement finding courts by name | Y | Y
Done | 2020-05-03 | WEB-0074 | Improve page layout - set header and footer to fixed position - set main content height to 100% with dynamic top and bottom paddings to prevent content from being covered by the heading or the footer | Improv |  | 1 |  | design: WEB-0074 - Improve page layout | Y | N
Done | 2020-08-21 12:09 | WEB-0073 | Add page footer for desktop | Feat | Medium | 1 |  | feat: WEB-0073 - Add page footer for desktop | Y | N
Done | 2020-05-08 | WEB-0072 | Move app navigator to the bottom of the screen for small screen - Make page-body-container height 100% - containers call app.mainDataIsLoaded to adjust sections of the page | Improv |  | 1 |  | improv: WEB-0072 - Move app navigator to the bottom of the screen for small screen | Y | N
Done | 2020-04-27 | WEB-0070 | Display User Details | Feat |  | 1 |  | feat: WEB-0070 - display user details | Y | Y | Displaying dummy data for City (WEB-0071)
Done | 2020-04-12 | WEB-0069 | Use single container for all auth module components | Refactor |  | 1 |  | refactor: WEB-0069 - Use single container for all auth module components | Y | N
Done | 2020-04-11 | WEB-0068 | Require email address when signing up | Improv |  | 1 |  | feat: WEB-0068 - require email address when signing up | Y | Y
Done | 2020-05-12 05:46 | WEB-0067 | Implement change password | Feat |  | 1 |  | feat: WEB-0067 - implement change password | Y | Y
Done | 2020-04-11 | WEB-0066 | Implement forgot password | Feat |  | 1 |  | FE: · feat: WEB-0066 - add functionality to reset forgotten password BE: · feat: WEB-0066 - add functionality to send password reset link to email · feat: WEB-0066 - add functionality to reset password | Y | Y
Done | 2020-03-03 | WEB-0065 | Implement password salting | Feat |  | 1 |  | feat: WEB-0065 - Implement password salting | N | Y
Done | 2020-03-30 | WEB-0064 | Improve behavior and add validations for Book Game modal | Improv |  | 1 |  | improv: WEB-0064 - Improve behavior and add validations for Book Game modal | Y | Y
Done | 2020-03-21 | WEB-0063 | Upon adding a game, focus the newly added entry in the calendar | Improv |  | 1 |  | improv: WEB-0063 - Upon adding a game, focus the newly added entry in the calendar | Y | N
Done | 2020-03-13 | WEB-0062 | Make Courts page the homepage | Refactor |  | 1 |  | refactor: WEB-0062 - Make Courts page the homepage | Y | N
Done | 2020-03-11 | WEB-0061 | Allow user to open court details in the same tab or in a new tab | Improv |  | 1 |  | improv: WEB-0061 - Allow user to open court details in the same tab or in a new tab | Y | N
Done | 2020-03-11 | WEB-0060 | Add game viewer container | Feat |  | 1 |  | feat: WEB-0060 - Add game viewer container | Y | N
Done | 2020-03-11 | WEB-0059 | Issue: Refresh token not working | Bug |  | 1 |  | fix: WEB-0059 - Issue: Refresh token not working | Y | N
Done | 2020-03-11 | WEB-0058 | Improve error handling function | Improv |  | 1 |  | improv: WEB-0058 - improve error handling function | Y | N
Done | 2020-03-11 | WEB-0057 | Add functionality to delete court photos | Feat |  | 1 |  | Feat: WEB-0057 - Add functionality to delete court photos | Y | Y
Done | 2020-03-08 | WEB-0056 | Display court images in a carousel | Feat |  | 1 |  | feat: WEB-0056 - Display court images in a carousel | Y | N
Done | 2020-03-08 | WEB-0055 | After adding an event, add the event to the calendar and make sure the event is visible | Improv |  | 1 |  | improv: WEB-0055 - After adding an event, add the event to the calendar and make sure the event is visible | Y | N
Done | 2020-03-08 | WEB-0054 | Events Calendar – Fix issue where Book Game modal is opened twice when a date is selected | Bug |  | 1 |  | fix: WEB-0054 - Events Calendar – Fix issue where Book Game modal is opened twice when a date is selected | Y | N
Done | 2020-03-08 | WEB-0053 | Events Calendar - Add a way for the use to navigate to a date using a date picker | Feat |  | 1 |  | feat: WEB-0053 - Events Calendar - Add a way for the use to navigate to a date using a date picker | Y | N
Done | 2020-03-08 | WEB-0052 | Add function to enforce authentication before running some code | Feat |  | 1 |  | feat: WEB-0052 - Add function to enforce authentication before running some code | Y | N
Done | 2020-03-08 | WEB-0051 | when user is redirected to login after a failed authentication, navigation is cancelled when a modal is open | Bug |  | 1 |  | fix: WEB-0051 - Fix issue: when user is redirected to login after a failed authentication, navigation is canelled when a modal is open | Y | N
Done | 2020-03-07 | WEB-0050 | Add functionality to book games and display list of games and schedule Also: included fix for WEB-0049 | Feat |  | 1 |  | feat: WEB-0050 - Add functionality to book games and display list of games and schedule | Y | Y
Done | 2020-03-07 | WEB-0049 | Do not log out user when calling refreshToken until authentication fails | Bug |  | 1 |  | feat: WEB-0050 - Add functionality to book games and display list of games and schedule | Y | N
Done | 2020-02-26 | WEB-0047 | Display court games in a new page | Feat |  | 1 |  | feat: WEB-0047 - display court games Also: - Added date component | Y | Y
Done | 2020-02-24 | WEB-0046 | Add Court Schedule page placeholder | Feat |  |  |  | feat: WEB-0046 - Add Court Schedule page placeholder | Y | N
Done | 2020-02-22 | WEB-0045 | Improve navigation design for wide screen | Improv |  | 1 |  | improv: WEB-0045 - Improve navigation design for wide screen | Y | N
Done | 2020-02-22 | WEB-0044 | Remove court seed to avoid resetting the profile photo url of test courts | Bug |  | 1 |  | fix: WEB-004 - Remove courts seed to avoid resetting the profile photo url of test courts | N | Y
Done | 2020-02-22 | WEB-0043 | Move app navigator in mobile toolbar | Improv |  | 1 |  | design: WEB-0043 - Move app navigator in mobile toolbar | Y | N
Done | 2020-02-20 | WEB-0041 | Redesign Courts page | Design |  | 1 |  | design: WEB-0041 - Redesign Courts page | Y | N
Done | 2020-02-20 | WEB-0040 | Implement custom theme Changes: · Added override for bootstrap’s _variable.scss file | Design |  | 1 |  | design: WEB-0040 - implement custom theme | Y | N
Done | 2020-02-17 | WEB-0039 | Add functionality to upload and display court photos | Feat |  | 1 |  | feat: WEB-0039 - add functionality to upload and display court photos | Y | Y
Done | 2020-02-17 | WEB-0038 | Add court photos page | Feat |  | 1 |  | · feat: WEB-0038 - add court photos state and placeholder Also: - added app navigator component · feat: WEB-0038 - display court photos | Y | Y
Done | 2020-02-16 | WEB-0037 | Modify code to use files from src folder when running Also: - place compiled .css files in src folder - modified .gitignore to ignore compiles css files in src folder | Setup |  | 1 |  | setup: WEB-0037 - modify code to use files from src folder when running Also: - place compiled .css files in src folder - modified .gitignore to ignore compiles css files in src folder | Y | N
Done | 2020-02-16 | WEB-0036 | Set up gulp watch | Setup |  | 1 |  | · setup: WEB-0036 - set up gulp watch · setup: exclude external libraries from gulp watch | Y | N
Done | 2020-02-13 | WEB-0035 | Restructured files (add SRC and DEST folders inside wwwroot) Also: - add gulp tasks to copy files to dest folder - use files from dest folder - add support for sass | Refactor |  | 1 |  | · refactor: WEB-0035 - restructured files (add SRC and DEST folders inside wwwroot) Also: - udpate gulp tasks - add support for sass · refactor: WEB-0035 - refactor authmodule components to use drbbly-default pattern (FE only) · refactor: WEB-0035 - modify code to use files from dest folder instead of src Also added gulp tasks for scripts and html (FE only) | Y | Y
Done | 2020-02-11 | WEB-0034 | Add functionality to update court’s primary photo | Feat |  | 1 |  | feat: WEB-0034 – add functionality to update a court’s primary photo | Y | Y
Done | 2020-02-22 | WEB-0032 | Redirect user to login page when refresh token is expired | Improv |  | 1 |  | improv: WEB-0032 - redirect to login when token is expired | Y | Y
Done | 2020-02-08 | WEB-0031 | Add Core project and SecurityUtility | Feat |  | 1 |  | feat: WEB-0031 – add Core project and SecurityUtility | N | Y
Done | 2020-02-09 | WEB-0031 | Court Viewer – Hide edit button when court is not owned by current user Additional changes: · Changed court owner id data type to String · Secured Court Registration API method · Fixed issues with Refresh · Token routine Redirect to court details after registration | Improv |  | 1 |  | improv: WEB-0031 – Hide edit button when court is not owned by current user Commits: https://github.com/rjpablo/Dribbly.WebClient/commit/66c2d04e9f72dd844c6306bd42c796916bedd42a https://github.com/rjpablo/DribblyAuthAPI/commit/869fcdaa28b888a011bb5f2f0910dbbe6dae6c8a | Y | Y
Done | 2020-02-08 | WEB-0030 | Implement Dependency Injection | Refactor |  | 1 |  | refactor: WEB-0030 – implement Dependency Injection | N | Y
Done | 2020-02-08 | WEB-0029 | Implement settings retrieval from db | Feat |  | 1 |  | feat: WEB-0029 – implement settings retrieval from db Includes BE changes for WEB-0028 | Y | Y
Done | 2020-02-08 | WEB-0028 | Add functionality to update court details | Feat |  | 1 |  | feat: WEB-0028 – add functionality to update court details | Y | Y (Forgot to commit)
Done | 2020-02-04 | WEB-0027 | Close modals on back button press | Improv |  | 1 |  | improv: WEB-0027 – Close modals on back button press | Y | N
Done | 2020-01-28 | WEB-0026 | Add court preview modal | Improv |  | 1 |  | feat: WEB-0026 – Add court preview modal | Y | N
Done | 2020-01-28 | WEB-0025 | Add Court Price and Book Now button in the footer | Feat |  | 1 |  | feat: WEB-0025 – Add Court Price and Book Now button in the footer | Y | N
Done | 2020-01-25 | WEB-0023 | Implemement automatic generation of templateUrl for all components | Improv |  | 1 |  | · feat: WE-0021 – Implement automatic generation of templateUrl for components · refactor: WEB-0023 – refactor components to use automatic generation of templateUrl | Y | N
Done | 2020-01-26 | WEB-0022 | Add court details page | Feat |  | 1
Done | 2020-01-25 | WEB-0021 | Implement automatic generation of templateUrl for components | feat |  | 1 |  | feat: WE-0021 – Implement automatic generation of templateUrl for components | Y | N
Done | 2020-01-24 | WEB-0020 | Add home link inside navigator | Improv |  | 1 |  | improv: WEB-0020 – add link to home in side navigator | Y | N
Done | 2020-01-24 | WEB-0019 | Display a default court photo if nothing was uploaded |  |  |  |  | improve: WEB-0019 – Display a default court photo if nothing was uploaded | Y | N
Done | 2020-09-28 | WEB-0017 | Make page navigator's position fixed on WEB | Improv | Medium | 1 |  | improv: WEB-0017 - Make page navigator's position fixed on WEB | Y | N
Done | 2020-01-23 | WEB-0016 | Fix overlay error (_status of undefine) | bug |  |  |  | fix: WEB-0016 – Fix overlay error (status of undefine) | Y | N
Done | 2020-01-23 | WEB-0015 | Improve Add Court functionality · Removed input of full address · Only store latLng for location · Made map search work · Moved location picker to the Add Court modal instead of showing another modal | improv |  |  |  | improv: WEB-0015 – Improve Add Court functionality | Y | Y
Done | 2020-01-21 | WEB-0014 | Add common features: · Alert and Confirmation dialog · Toast Notifications · Basic error handling · Log out confirmation dialog | feat |  |  |  | feat: WEB-0014 – Add common features
Done | 2020-01-19 | WEB-0013 | Add feature for selecting an address from a map | improv |  |  |  | Branch: feat-web-0013-add-location-picker
Done | 2020-01-18 | WEB-0012 | Add overlays when loading data | Feat |  |  |  | feat: WEB-0012 – add overlay directive to display when loading content
Done | 2020-01-18 | WEB-0009 | Add court registration feature | feat |  |  |  | feat: WEB-0009 – add court registration functionality | Y | Y
Done | 2020-01-17 | WEB-0007 | Set toolbar items based on current page | feat |  |  |  | feat: WEB-0007 - set toolbar items based on current page | Y | N
Done | 2020-01-16 | WEB-0006 | Restructure app | Refactor |  |  |  | refactor: WEB0006 – enhance file structure and apply naming convention to main module | Y | N
Done | 2020-01-05 | WEB-0005 | Convert courtListItem photo into a reusable component | Refactor |  |  |  | refactor: convert courtListItem photo into a reusable component | Y | N
Done | 2020-01-05 | WEB-0004 | Display list of Featured courts using dummy data | Feat |  |  |  | feat: WEB0004 – display list of featured courts using dummy data | Y | Y
Done | 2020-01-12 | WEB-0003 | Update title based on state | Improv |  |  |  | improv-web-0003-update-title-based-on-state
Done | 2020-01-27 | WEB-00024 | Make site footer stick to the bottom of the screen. Also made logged out menubar stay inside site footer | Improv |  | 1 |  | improv: WEB-0024 – make site footer stick to the bottom of the screen Also make logged out menubar stay inside site footer | Y | N
Done | 2020-01-11 | WEB-0002 | Implement sidebar navigation | Feat |  |  |  | feat: WEB-0002 - implement side navigator
Done | 2019-10-13 | WEB-0001 | Implement refresh tokens | Feat |  |  |  | feat-web-0001-implement-refresh-tokens
Note on F1: Critical - show stopper / causes further issues if not fixed immediately High - must be completed before deployment Medium - causes a bit of inconveniece/nice to have before deployment Low - not causing inconvenience / improvement / for phase 2