## Sheet1
Task ID | Type | For Phase 1 | Description | Commit Message | Has FE Changes | Has BE Changes | Status
WEB-0069 | Refactor | Y | Use single container for all auth module components | refactor: WEB-0069 - Use single container for all auth module components | Y | N | Done (04/12/2020)
WEB-0068 | Improv | Y | Require email address when signing up | feat: WEB-0068 - require email address when signing up | Y | Y | Done (04/11/2020)
WEB-0067 |  |  | Implement change password
WEB-0066 | Feat | Y | Implement forgot password | FE: · feat: WEB-0066 - add functionality to reset forgotten password BE: · feat: WEB-0066 - add functionality to send password reset link to email · feat: WEB-0066 - add functionality to reset password | Y | Y | Done (04/11/2020)
WEB-0065 | Feat | Y | Implement password salting | feat: WEB-0065 - Implement password salting | N | Y | Done (03/03/2020)
WEB-0064 | Improv | Y | Improve behavior and add validations for Book Game modal | improv: WEB-0064 - Improve behavior and add validations for Book Game modal | Y | Y | Done (30/03/2020)
WEB-0063 | Improv | Y | Upon adding a game, focus the newly added entry in the calendar | improv: WEB-0063 - Upon adding a game, focus the newly added entry in the calendar | Y | N | Done (21/03/2020)
WEB-0062 | Refactor | Y | Make Courts page the homepage | refactor: WEB-0062 - Make Courts page the homepage | Y | N | Done (13/03/2020)
WEB-0061 | Improv | Y | Allow user to open court details in the same tab or in a new tab | improv: WEB-0061 - Allow user to open court details in the same tab or in a new tab | Y | N | Done (11/03/2020)
WEB-0060 | Feat | Y | Add game viewer container | feat: WEB-0060 - Add game viewer container | Y | N | Done (11/03/2020)
WEB-0059 | Fix | Y | Issue: Refresh token not working | fix: WEB-0059 - Issue: Refresh token not working | Y | N | Done (03/11/2020)
WEB-0058 | Improv | Y | Improve error handling function | improv: WEB-0058 - improve error handling function | Y | N | Done (03/11/2020)
WEB-0057 | Feat | Y | Add functionality to delete court photos | Feat: WEB-0057 - Add functionality to delete court photos | Y | Y | Done (03/11/2020)
WEB-0056 | Feat | Y | Display court images in a carousel | feat: WEB-0056 - Display court images in a carousel | Y | N | Doone (03/08/2020)
WEB-0055 | Improv | Y | After adding an event, add the event to the calendar and make sure the event is visible | improv: WEB-0055 - After adding an event, add the event to the calendar and make sure the event is visible | Y | N | Done (03/08/2020)
WEB-0054 | Fix | Y | Events Calendar – Fix issue where Book Game modal is opened twice when a date is selected | fix: WEB-0054 - Events Calendar – Fix issue where Book Game modal is opened twice when a date is selected | Y | N | Done (03/08/2020)
WEB-0053 | Feat | Y | Events Calendar - Add a way for the use to navigate to a date using a date picker | feat: WEB-0053 - Events Calendar - Add a way for the use to navigate to a date using a date picker | Y | N | Done (03/08/2020)
WEB-0052 | Feat | Y | Add function to enforce authentication before running some code | feat: WEB-0052 - Add function to enforce authentication before running some code | Y | N | Done (03/08/2020)
WEB-0051 | Fix | Y | when user is redirected to login after a failed authentication, navigation is cancelled when a modal is open | fix: WEB-0051 - Fix issue: when user is redirected to login after a failed authentication, navigation is canelled when a modal is open | Y | N | Done (03/08/2020)
WEB-0050 | Feat | Y | Add functionality to book games and display list of games and schedule Also: included fix for WEB-0049 | feat: WEB-0050 - Add functionality to book games and display list of games and schedule | Y | Y | Done (03/07/2020)
WEB-0049 | Fix | Y | Do not log out user when calling refreshToken until authentication fails | feat: WEB-0050 - Add functionality to book games and display list of games and schedule | Y | N | Done (03/07/2020)
WEB-0048 | Fix | Y | Court Photos page title is incorrect |  |  |  | Pending
WEB-0047 | Feat | Y | Display court games in a new page | feat: WEB-0047 - display court games Also: - Added date component | Y | Y | Done (02/26/2020)
WEB-0046 | Feat |  | Add Court Schedule page placeholder | feat: WEB-0046 - Add Court Schedule page placeholder | Y | N | Done (02/24/2020)
WEB-0045 | Improve | Y | Improve navigation design for wide screen | improv: WEB-0045 - Improve navigation design for wide screen | Y | N | Done (20200223)
WEB-0044 | Fix | Y | Remove court seed to avoid resetting the profile photo url of test courts | fix: WEB-004 - Remove courts seed to avoid resetting the profile photo url of test courts | N | Y | Done (02/22/2020)
WEB-0043 | Improve | Y | Move app navigator in mobile toolbar | design: WEB-0043 - Move app navigator in mobile toolbar | Y | N | Done (02/22/2020)
WEB-0042 | Feat | Y | Courts – use featured courts as background instead of a static bg image. Also autoscroll thru featured courts
WEB-0041 | Design | Y | Redesign Courts page | design: WEB-0041 - Redesign Courts page | Y | N | Done (02/20/2020)
WEB-0040 | Design | Y | Implement custom theme Changes: · Added override for bootstrap’s _variable.scss file | design: WEB-0040 - implement custom theme | Y | N | Done (02/20/2020)
WEB-0039 | Feat | Y | Add functionality to upload and display court photos | feat: WEB-0039 - add functionality to upload and display court photos | Y | Y | Done (02/17/2020)
WEB-0038 | Feat | Y | Add court photos page | · feat: WEB-0038 - add court photos state and placeholder Also: - added app navigator component · feat: WEB-0038 - display court photos | Y | Y | Done (02/172020)
WEB-0037 | Setup | Y | Modify code to use files from src folder when running Also: - place compiled .css files in src folder - modified .gitignore to ignore compiles css files in src folder | setup: WEB-0037 - modify code to use files from src folder when running Also: - place compiled .css files in src folder - modified .gitignore to ignore compiles css files in src folder | Y | N | Done (02/16/2020)
WEB-0036 | Setup | Y | Set up gulp watch | · setup: WEB-0036 - set up gulp watch · setup: exclude external libraries from gulp watch | Y | N | Done (02/16/2020)
WEB-0035 | Refactor | Y | Restructured files (add SRC and DEST folders inside wwwroot) Also: - add gulp tasks to copy files to dest folder - use files from dest folder - add support for sass | · refactor: WEB-0035 - restructured files (add SRC and DEST folders inside wwwroot) Also: - udpate gulp tasks - add support for sass · refactor: WEB-0035 - refactor authmodule components to use drbbly-default pattern (FE only) · refactor: WEB-0035 - modify code to use files from dest folder instead of src Also added gulp tasks for scripts and html (FE only) | Y | Y | Done (02/13/2020)
WEB-0034 | Feat | Y | Add functionality to update court’s primary photo | feat: WEB-0034 – add functionality to update a court’s primary photo | Y | Y | Done (02/11/2020)
WEB-0033 | Fix | Y | Court Edit – Modal title is wrong |  |  |  | Pending
WEB-0032 | Improve | Y | Redirect user to login page when refresh token is expired | improv: WEB-0032 - redirect to login when token is expired | Y | Y | Done (02/22/2020)
WEB-0031 | Feat | Y | Add Core project and SecurityUtility | feat: WEB-0031 – add Core project and SecurityUtility | N | Y | Done (02/08/2020)
WEB-0031 | Improv | Y | Court Viewer – Hide edit button when court is not owned by current user Additional changes: · Changed court owner id data type to String · Secured Court Registration API method · Fixed issues with Refresh · Token routine Redirect to court details after registration | improv: WEB-0031 – Hide edit button when court is not owned by current user Commits: https://github.com/rjpablo/Dribbly.WebClient/commit/66c2d04e9f72dd844c6306bd42c796916bedd42a https://github.com/rjpablo/DribblyAuthAPI/commit/869fcdaa28b888a011bb5f2f0910dbbe6dae6c8a | Y | Y | Done (02/09/2020)
WEB-0030 | Refactor | Y | Implement Dependency Injection | refactor: WEB-0030 – implement Dependency Injection | N | Y | Done (02/08/2020)
WEB-0029 | Feat | Y | Implement settings retrieval from db | feat: WEB-0029 – implement settings retrieval from db Includes BE changes for WEB-0028 | Y | Y | Done (02/08/2020)
WEB-0028 | Feat | Y | Add functionality to update court details | feat: WEB-0028 – add functionality to update court details | Y | Y (Forgot to commit) | Done (02/08/2020)
WEB-0027 | Improv | Y | Close modals on back button press | improv: WEB-0027 – Close modals on back button press | Y | N | 2020-02-04
WEB-0026 | Improve | Y | Add court preview modal | feat: WEB-0026 – Add court preview modal | Y | N | Done (01/28/20)
WEB-0025 | Feat | Y | Add Court Price and Book Now button in the footer | feat: WEB-0025 – Add Court Price and Book Now button in the footer | Y | N | Done (01/28/20)
WEB-0023 | Improv | N | Implemement automatic generation of templateUrl for all components | · feat: WE-0021 – Implement automatic generation of templateUrl for components · refactor: WEB-0023 – refactor components to use automatic generation of templateUrl | Y | N | Done (01/25/20)
WEB-0022 | Feat | Y | Add court details page |  |  |  | Done (01/26/20)
WEB-0021 | feat | Y | Implement automatic generation of templateUrl for components | feat: WE-0021 – Implement automatic generation of templateUrl for components | Y | N | Done (01/25/20)
WEB-0020 | Improv | Y | Add home link inside navigator | improv: WEB-0020 – add link to home in side navigator | Y | N | Done (01/24/20)
WEB-0019 |  |  | Display a default court photo if nothing was uploaded | improve: WEB-0019 – Display a default court photo if nothing was uploaded | Y | N | Done (01/24/20)
WEB-0018 | Bug | Y | Fix bug: a place is returned by map autocomplete when inputing “la kdfld” and pressing enter, even when there is no selected suggestion |  |  |  | Pending
WEB-0017 | feat | Y | Add page toolbar for Web version |  |  |  | Pending
WEB-0016 | bug |  | Fix overlay error (_status of undefine) | fix: WEB-0016 – Fix overlay error (status of undefine) | Y | N | Done (01/23/20)
WEB-0015 | improv |  | Improve Add Court functionality · Removed input of full address · Only store latLng for location · Made map search work · Moved location picker to the Add Court modal instead of showing another modal | improv: WEB-0015 – Improve Add Court functionality | Y | Y | Done (01/23/20)
WEB-0014 | feat |  | Add common features: · Alert and Confirmation dialog · Toast Notifications · Basic error handling · Log out confirmation dialog | feat: WEB-0014 – Add common features |  |  | Done (01/21/20)
WEB-0013 | improv |  | Add feature for selecting an address from a map | Branch: feat-web-0013-add-location-picker |  |  | Done
WEB-0012 | Feat |  | Add overlays when loading data | feat: WEB-0012 – add overlay directive to display when loading content |  |  | Done (01/18/20)
WEB-0011 | Feat | Y | Add “Talk to us” link to FB page |  |  |  | Pending
WEB-0010 | Bug | Y | Fix issue: toolbar items get set multiple times when logging in and out of the app because toolbars onSetItems handler gets registered everytime it is initialized |  |  |  | Pending
WEB-0009 | feat |  | Add court registration feature | feat: WEB-0009 – add court registration functionality | Y | Y | Done (01/18/20)
WEB-0008 | feat |  | Create i18n directive
WEB-0007 | feat |  | Set toolbar items based on current page |  | Y | N | Done
WEB-0006 | Refactor |  | Restructure app | refactor: WEB0006 – enhance file structure and apply naming convention to main module | Y | N | Done (01/16/2020)
WEB-0005 | Refactor |  | Convert courtListItem photo into a reusable component | refactor: convert courtListItem photo into a reusable component | Y | N | Done (01/05/2020)
WEB-0004 | Feat |  | Display list of Featured courts using dummy data | feat: WEB0004 – display list of featured courts using dummy data | Y | Y | Done (01/05/2020)
WEB-0003 | Improv |  | Update title based on state | improv-web-0003-update-title-based-on-state |  |  | Done (01-12-2020)
WEB-00024 | Improv | Y | Make site footer stick to the bottom of the screen. Also made logged out menubar stay inside site footer | improv: WEB-0024 – make site footer stick to the bottom of the screen Also make logged out menubar stay inside site footer | Y | N | Done (01/27/20)
WEB-0002 | Feat |  | Implement sidebar navigation |  |  |  | Done
WEB-0001 | Feat |  | Implement refresh tokens | feat-web-0001-implement-refresh-tokens |  |  | Done